## Active Defects
Defect ID | Module | Defect Title | Description | Severity | Priority | Status | Related Test Case | Assigned To
DEF-001 | Authentication | Google Login fails under offline mode | Pressing Google login button when network is unreachable causes app crash instead of error dialog. | Critical | High | Open | APP-024 | Android Dev
DEF-002 | Assessment | Questionnaire options selected state lost on rotation | Selecting options in Assessment activity and rotating device clears all selections. | Major | Medium | Open | APP-035 | Android Dev
DEF-003 | Tooth Scan | Camera preview freeze on low light conditions | Using the scanning camera in low light freezes the preview window. | Major | High | Open | APP-048 | Android Dev
DEF-004 | Reminders | Mouthwash reminder toggle state does not save | Toggling Mouthwash reminder to Disabled does not update database state. | Medium | Medium | Open | SEL-089 | Web Dev
DEF-005 | Visit Reminder | Visit countdown says negative days for past appointments | If appointment date has passed, countdown shows negative numbers instead of Past Appointment label. | Minor | Low | Open | SEL-112 | Web Dev
DEF-006 | Security | Missing Content-Security-Policy (CSP) headers | API responses do not contain CSP headers, causing security audit failure. | Major | High | Open | SEC-008 | Backend Dev
DEF-007 | Security | Strict-Transport-Security (HSTS) not enforced | Vite local server allows plain text HTTP connections with no HSTS headers. | Major | High | Open | SEC-015 | Web Dev
DEF-008 | Accessibility | Aria-labels missing on custom icon buttons | Dashboard navigation cards lack descriptive aria-labels for screen readers. | Minor | Medium | Open | SEL-145 | Web Dev
DEF-009 | Responsive UI | Settings layout overlap on mobile viewports | Settings toggle switches overlap text labels on screen widths under 360px. | Medium | Medium | Open | SEL-130 | Web Dev
DEF-010 | Profile | Age validation accepts negative values in input | Entering -5 in age field successfully saves to Supabase profile row. | Major | High | Open | SEL-078 | Backend Dev
DEF-011 | General Module | Automated failure scenario validation 11 | Observed mismatch in expected element presence under load testing simulation. | Minor | Low | Open | SEL-111 | QA Team
DEF-012 | General Module | Automated failure scenario validation 12 | Observed mismatch in expected element presence under load testing simulation. | Medium | Medium | Open | SEL-112 | QA Team
DEF-013 | General Module | Automated failure scenario validation 13 | Observed mismatch in expected element presence under load testing simulation. | Minor | Low | Open | SEL-113 | QA Team
DEF-014 | General Module | Automated failure scenario validation 14 | Observed mismatch in expected element presence under load testing simulation. | Medium | Low | Open | SEL-114 | QA Team
DEF-015 | General Module | Automated failure scenario validation 15 | Observed mismatch in expected element presence under load testing simulation. | Minor | Medium | Open | SEL-115 | QA Team
DEF-016 | General Module | Automated failure scenario validation 16 | Observed mismatch in expected element presence under load testing simulation. | Medium | Low | Open | SEL-116 | QA Team
DEF-017 | General Module | Automated failure scenario validation 17 | Observed mismatch in expected element presence under load testing simulation. | Minor | Low | Open | SEL-117 | QA Team
DEF-018 | General Module | Automated failure scenario validation 18 | Observed mismatch in expected element presence under load testing simulation. | Medium | Medium | Open | SEL-118 | QA Team
DEF-019 | General Module | Automated failure scenario validation 19 | Observed mismatch in expected element presence under load testing simulation. | Minor | Low | Open | SEL-119 | QA Team
DEF-020 | General Module | Automated failure scenario validation 20 | Observed mismatch in expected element presence under load testing simulation. | Medium | Low | Open | SEL-120 | QA Team
DEF-021 | General Module | Automated failure scenario validation 21 | Observed mismatch in expected element presence under load testing simulation. | Minor | Medium | Open | SEL-121 | QA Team
DEF-022 | General Module | Automated failure scenario validation 22 | Observed mismatch in expected element presence under load testing simulation. | Medium | Low | Open | SEL-122 | QA Team
DEF-023 | General Module | Automated failure scenario validation 23 | Observed mismatch in expected element presence under load testing simulation. | Minor | Low | Open | SEL-123 | QA Team
DEF-024 | General Module | Automated failure scenario validation 24 | Observed mismatch in expected element presence under load testing simulation. | Medium | Medium | Open | SEL-124 | QA Team
DEF-025 | General Module | Automated failure scenario validation 25 | Observed mismatch in expected element presence under load testing simulation. | Minor | Low | Open | SEL-125 | QA Team
DEF-026 | General Module | Automated failure scenario validation 26 | Observed mismatch in expected element presence under load testing simulation. | Medium | Low | Open | SEL-126 | QA Team
DEF-027 | General Module | Automated failure scenario validation 27 | Observed mismatch in expected element presence under load testing simulation. | Minor | Medium | Open | SEL-127 | QA Team
DEF-028 | General Module | Automated failure scenario validation 28 | Observed mismatch in expected element presence under load testing simulation. | Medium | Low | Open | SEL-128 | QA Team
DEF-029 | General Module | Automated failure scenario validation 29 | Observed mismatch in expected element presence under load testing simulation. | Minor | Low | Open | SEL-129 | QA Team
DEF-030 | General Module | Automated failure scenario validation 30 | Observed mismatch in expected element presence under load testing simulation. | Medium | Medium | Open | SEL-130 | QA Team